## Sheet1
Summary | Issue Type | Status | Assignee | Description | Sprint | Client Approval | Client Comments
Design UI/Theme - As a User, I should be able to login to see my progress/data | US | IN-PROGRESS | S538339@nwmissouri.edu | Acceptance Criteria: 1.User should be able to redirect to the user's home page when logins into the app. | 1
Design UI/Theme - As a User,I should be able to login to access the app and my data/progress | SUB-TASK | IN-PROGRESS | S538306@nwmissouri.edu | Acceptance Criteria: 1.A login page should contain username and password input fields. 2.Logo of the app should be on top of the page. 3.If useremailid is empty ,it should throw an error as its a required field. 4.If password is empty ,it should throw an error as its a required field. 5.A User should be able to login into app and able to look at his data progress like his step count and user settings. 6.Start developing the User page so that user can login to see user home page. 7.User should able to see data once he/she logins. 8.User should be able to enter emailID and password to login. 9.User can access forgot password page when he clicks on it. 10.User should be asked to enter emailID to send a verification code. 11.User should be able to reset the password. 12.User should be able to redirect to home page | 1
Design Data- As a user, I want to have a look at my profile so that, I can update any necessary information. | US | IN-PROGRESS | S538107@nwmissouri.edu | Acceptance criteria: 1. Name must be provided by the user and it is editable. 2. Users must add his date of birth too as it is a mandatory field. 3. Users can update if they have any medical conditions. 4. Height and Weight are the features to be edited by the user. 5. The phone number can be editable by the user. 6. The number should contain at least ten characters including the area code. 7. The phone number should be a valid number 8. The user can mention his main activity of the app to track, which can be updated in the daily activity attribute field. | 1
Design Data- As a user, I want to reset my password, so that I can access my account again | US | IN-PROGRESS | S538408@nwmissouri.edu | Acceptance criteria: 1.User will enter his/her email to find the account linked to it so that a verification code will be sent to their mail. 2. User must enter the verification code sent to their mail id so that they can reset the password 3. User must provide a new password with validations of the password having a length of at least 8-16 characters including at least 1 special character and a number. 4. user must submit and so that data is stored and now they can try accessing their account. | 1
Design Architecture- As an Admin, I need to have full access to open the Admin page. | US | IN-PROGRESS | S538363@nwmissouri.edu | Acceptance Criteria: As an Admin, I need to have full access to open the Admin page. Assignee needs to deploy the admin page after the whole set of development. 1.A login page should contain a link to login to the admin interface. 2.The logo of the app should be on top of the page. 3.If the admin email id is empty, it should throw an error as its a required field. 4.If the password is empty, it should throw an error as its a required field. 5.An admin should be able to login to the app and able to look at the whole user's data progress like his step count and user settings. 6.Admin should have the privilege to edit any data to the user | 1
Design Architecture - As a User, Deploying user login page in google clouds | US | IN-PROGRESS | S538103@nwmissouri.edu | Acceptance Criteria: 1.Deploy the user login page in Heroku/Google clouds. 2.When the user directs to the URL should be able to view the UI with 2 fields mainly username and password. 3.Users should view clickable buttons like login. when the user clicks login should be able to route to the homepage. 4.Also, Users should be able to view 2 other buttons like forget password and register. | 1